## generate sharable link estimati
SNo | Feature / Activity details | Task Description | Backend Development
1 | Design share_links schema & indexes | - Create new MongoDB collection share_links - Add indexes | 1
2 | Secure token generation (crypto) | - generate unique token - Integrate into link creation flow | 3
3 | Create Share Link API | - Validate input feilds - Fetch resources - Apply config (expiryAt) - Store link in DB - Return generated URL | 6
4 | Access Share Link (validation + response) | - Validate token (exists, active, not expired) - validate password if entered - Fetch resource (file/folder) - Return structured response | 8
5 | Access logs (IP, timestamp) | - Capture logs trigger on every link access | 2
Front End Estimates
6 | Add "Share via Link" to Folder Dropdown | handle event in list for modal opening | 1
| Add menu item | Add in document-row-card.component.html after History
| Add @Output() shareFolder | emitter in document-row-card.component.ts
| Handle emit | In document-list.component.ts to open modal
7 | Share Link Generation Modal | with generate api integration and ui, functionality | 6
| Create modal | share-folder-link-modal
| Form fields | Validity (1/7/15 days), Download/Reshare toggles, Password
| Generate Link | Button calls API and displays generated URL
| Clipboard | Copy to clipboard button functionality
| Notifications | Success/error toast using isSuccessToster pattern
| Service Method | Add generateShareLink in DocumentValutService
8 | Public Access Page - Login Modal | with validate api integration and ui | 4
| Create component | shared-folder-access (no auth guard)
| Routing | Add /shared-folder/:token outside auth guard
| Entry Modal | On load show modal for Name and Password
| Validation | Call validate API and store temp token on success
| Error Handling | Show inline error message on failure
| Service Method | Add validateShareLink in DocumentValutService
9 | Shared Folder View | handle pagination and nested folders | 6
| Logic Reuse | Reuse document-list logic in restricted public context
| Layout | Hide sidebar using hideNavBar pattern (HomeLayoutComponent)
| Download Flag | Conditionally show/hide Download based on allowDownload
| Reshare Flag | Conditionally show/hide Share based on allowReshare
| Restrictions | Remove Edit, Delete, and Upload actions
| Navigation | Handle nested folders with existing scroll/pagination
| Constants | Add SharedFolderAccess route in routes.constants.ts
10 | Testing |  | 4
| Permissions | Verify all combinations of share link permissions
| Validation | Test success, wrong password, and expired links
| View Restrictions | Verify download/reshare flag logic in public view

## Sheet1
Already exists |  | Dev Status | QA Status
Upload scanned invoice for each Unique ID |  |  | not working properly
Assumption: GRN contains invoice details
Configurable approval workflow levels |  |  | working ( we can add user and department also in same level )
User selects approvers at each level |  |  | working but only one user can approve
Notifications to approvers |  |  | not getting properly
Approval moves transaction forward
Rejection handling |  |  | working ( stage by stage rejection only )
Configurable user-level restrictions
Workflow progress view |  |  | working.
Transaction list with color coding
Expected user load (100–120 users)
Need to implement
Assumption: GRN contains invoice details
Multiple approvers at the same level | Implement (drop down of options all the users should approve or anyone by default anyone to be selected)
Invoice / PO details sent from SAP as GRN
Invoice number validation (TBD)
Unique number generation per GRN
GRN details integrated into Invoice Tracking System
Each GRN is processed separately
if reject Goes back to the creator | c
Dashboard
Analytics (PDF & Excel)

## estimations
SNo | Feature / Activity details | Requirement Description | Backend Development | Frontend Development
1 | Dashboard | pie chart based on the status and branch wise | 1 | 4
|  | registered transactions will be displayed in a table format(all and status based) | 1 | 4
|  | download the transaction list as a PDF | 3 | 1
|  | download the transaction list as an Excel file. | 1 | 1
2 | approve flow | Multiple approvers at the same level | 6
3 | Workflow Rejection flow | If reject goes back to the creator | 2